## Step - 1
S. No | Global Reference ID | Atomic Steps Reference ID | Setup Step (Action) | Setup Step Description | 4 Substeps | Decision Group | Decision to be Made Before Setup Step | Decision Category | Why This Matters | Mobile App First Implication | UX Translation | Data Requirement | User Interaction / Flow Impact | Dashboard / Interface Implication | What Standardized Must Be Done | Atomic Reusability | Common Library to Store | GCP / BigQuery Alignment | Sequence Order | Estimated Time Required | Expected Output | Completion Measures | Dependencies | Mobile-First & Responsive UX Google Material Design Decision | Mobile-First & Responsive UI Google Material Design Decision | Mobile-First & Responsive UX Google Material Design Implementation | Mobile-First & Responsive UI Google Material Design Implementation | Domain Expertise Needed | Mistake-Proofing (Poka-Yoke) | Self-Chasing | What Creates Vitality & Prosperity For Us | What Creates Vitality & Prosperity For the Customer | Responsive UX/UI Design | Vitality & Prosperity (VAP) | Setup Step (Action).1 | Atomic Step | Metric Name | Floor Boundary | Optimal Target | Ceiling Boundary | Best Qualitative Output | Best Qualitative/Quantitative Output Type | Assigned Team Member | Data Collected by System | Required Data / Configuration / Implementation Fields (from AL-AQ Analysis) | Dependency Count | Dependency (Atomic Step Serial No) | Output format
351 | BPTR-0498 | BPTR-0498-A01 | Implement Offline Sync State Icon. | Open the primary mobile application assets folder layout. | 1. Select offline icon (cloud with slash). 2. Define sync pending badge count. 3. Design "Reconnecting" animation. 4. Set persistent placement logic. | Tech | Configure service workers logic. | Interaction | In remote working environments, internet drops happen. UI must clearly indicate data is saved locally and waiting to sync. | Absolutely critical for 5G/4G connectivity drops while commuting or on-site. | Persistent header icon tracking local storage vs cloud sync. | Atomic-level data fields: Layout Type; Layout Grid Dimensions; Spacing Rules; Alignment Settings; Layout Validation Status ¦¦ No matched reference row in Setup Implementation master list — required data fields limited to atomic-level Data Collection Requirements only; standardized Mobile UX/UI & domain-expertise fields unavailable, verify manually. | Users confidently continue working offline without fear of data loss. | Added to global application shell header. | Offline state visual tokens. | Global application state. | System State Patterns. | Client-side cache sync management. | Level 13 ¦ Phase: EXECUTION ¦ Atomic Step: 1.0 ¦ Row: 351.0 | 3 hours | Offline/Syncing icon state specifications. | Distinct visual difference between connected and queued states. |  | Essential for mobile workers in variable network conditions. | SVG icon updates driven by browser navigator.onLine API. | Prevents data-loss anxiety. | React state binding to network events. | Tech | System physically blocks page refresh if sync queue > 0, preventing accidental cache wipe. | When connection restores, icon pulses green until queue hits 0, chasing user to keep tab open. For Vitality and Prosperity give: | Stops users from refreshing and double-querying DB. | Smooth, professional system experience. |  |  | Implement Offline Sync State Icon. | Open the primary mobile application assets folder layout. | Requirements Traceability Coverage | 90.0 | 98.0 | 100.0 | Complete (Scale: Complete/Partial/Not Complete) | Confirm the source-of-truth document is the latest approved version and every referenced field/rule is traceable back to it before proceeding. | Pooja | Layout Type; Layout Grid Dimensions; Spacing Rules; Alignment Settings; Layout Validation Status; Completion Status ('Complete (Scale: Complete/Partial/Not Complete)'); Action/Event Timestamp; User/Session ID | Data Required: Requirements Traceability Coverage ¦¦ Configuration Data: Floor=90 ¦ Optimal=98 ¦ Ceiling=100 ¦¦ Implementation Data: Output field='Complete (Scale: Complete/Partial/Not Complete)'; Standard/Reference='Confirm the source-of-truth document is the latest approved version and every referenced field/rule is traceable back to it before proceeding.' | 0 | No Dependency

## Microstep
MS ID | Starting Point | Prerequisites | Responsible Role | Exact Implementation Action | Execution Method/Tool | Dependency Check | Expected Output | Validation Method | Completion Evidence | Blocker Condition
Atomic Step Ref ID: BPTR-0498-A01 ¦ Setup Step: Implement Offline Sync State Icon. ¦ Atomic Step: Open the primary mobile application assets folder layout.
BPTR-0498-A01-M1 | Mobile app repo, primary assets directory (e.g. /src/assets/icons/) | Repo access; known asset-folder convention | Frontend Developer (React) | Pull latest repo and open the primary assets folder where icon/SVG assets live | git pull; navigate to /src/assets/icons | Folder exists, follows the project's icon-naming convention | Assets folder open, structure confirmed | Review folder listing for naming convention (ic_<name>.svg) | Folder listing screenshot attached | Assets folder missing/misnamed — escalate to Tech lead
BPTR-0498-A01-M2 | Opened assets folder | M1 complete | Frontend Developer (React) | Retrieve the source-of-truth requirements for the icon (select icon, badge count, "Reconnecting" animation, placement logic) and confirm the doc is the latest approved version | Compare the 4 substeps against the requirements doc's revision history | Doc version = latest approved; all 4 substeps traceable to an explicit requirement line | Traceability checklist mapping each substep to its requirement | Manual line-by-line trace of each substep | Traceability checklist attached, coverage % calculated | Doc outdated/unapproved, or a substep untraceable — escalate to Tech/Product
BPTR-0498-A01-M3 | Traceability checklist from M2 | M1 & M2 complete | Frontend Developer (React) | Confirm the assets folder is collision-free for the planned new icon file names (e.g. ic_offline_sync.svg, ic_reconnecting.svg) | Search assets folder for existing files with matching/similar names | No naming collisions found | Confirmation the folder is clear and ready | File search returns no conflicts | Search result screenshot/log attached | Conflicting file with same name exists — must be resolved first
BPTR-0498-A01-M4 | Outputs of M1–M3 | All prior micro-steps complete | Frontend Developer (React) | Calculate and log the final Requirements Traceability Coverage score and Complete/Partial/Not Complete status | Coverage % = traced substeps ÷ 4; update ticket's Completion Status field | Coverage ≥90% (floor) to mark Complete | Logged coverage score and status | Peer review of calculation | Ticket updated with status + coverage % + checklist attached | Coverage <90% — missing approvals must be gathered first

## Decomposed Microstep
Implementation Step Name | Atomic Step Name | Micro Atomic Step Name | Frontend Objective | Technical Implementation Goal | User Trigger & Feature Scenario | Event Handler & User Interaction | DOM Render & UI State Outcome | Mobile-First CSS/Layout Strategy | Responsive Media Queries & Breakpoint Logic | Google Material Design 3 UI Library Imports & Components | Atomic Component Hierarchy | Component Architecture & File Structure | Flexbox/Grid CSS Layout Specifications | CSS Spacing Tokens & Alignment Rules | CSS Typography & Font Token Application | CSS Theme Variables, Dark Mode & Z-Index/Elevation | Icon Components & SVG Asset Optimization | Pseudo-Classes & Component State Machine | CSS Transitions, Keyframes, or Animation Library Logic | Interactive Logic & Gamification Hooks | Accessibility (a11y) Markup | Client-Side Input Validation Logic & Guardrails | Conditional Rendering & Fallbacks | Toast/Banner Notification Logic & Success Feedback | Router Integration & Navigation State Management | String Constants & i18n/Localization Keys | Edge Case Guard Clauses & Async Error Catching | Component Props Interface & Reusable Variants | Figma-to-Code Mapping & Styling Approach | API Contracts, Data Fetching & State Data Flow | Package Dependencies, Performance Budget & Browser Support | Definition of Done, Unit/Integration Testing & QA Checklist
Implement Offline Sync State Icon | BPTR-0498-A01 — Open the primary mobile application assets folder layout | BPTR-0498-A01-M1 — Pull repo and open primary assets folder | Not Applicable — file/folder discovery, no user-facing outcome yet | Confirm the primary assets directory (/src/assets/icons/) exists and follows the icon-naming convention before new icon assets are added | Not Applicable | Not Applicable — CLI/IDE action | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Confirms the assets folder location within the app shell structure where the future offline-sync icon component will source its SVGs | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Guard: assets folder missing or misnamed halts progress — escalate to Tech lead | Not Applicable | Not Applicable | Not Applicable | Not Applicable | DoD: folder listing reviewed for ic_<name>.svg naming convention; folder listing screenshot attached
|  | BPTR-0498-A01-M2 — Retrieve and trace icon requirements to approved documentation | Ensure the offline/sync icon eventually built (cloud-with-slash icon, badge count, Reconnecting animation, placement) is built against real, approved requirements — not assumptions | Trace all 4 substeps (select icon, define badge count, design Reconnecting animation, set placement logic) to explicit lines in the latest-approved requirements doc | Represents the future scenario of a mobile worker losing connectivity and needing a persistent visual cue that data is saved locally and queued to sync | Not Applicable — requirements tracing, event handlers not yet built | Not Applicable — no rendering yet, this is a documentation trace | Not Applicable — layout not authored yet | Not Applicable — breakpoints not yet relevant | Not Applicable — components not yet selected/imported | Not Applicable — hierarchy not yet defined | Not Applicable — no file structure created yet, only requirements traced | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Guard: doc outdated/unapproved, or any of the 4 substeps untraceable to an explicit requirement — escalate to Tech/Product before proceeding | Not Applicable | Not Applicable | Not Applicable | Not Applicable | DoD: traceability checklist maps all 4 substeps to explicit requirement lines, doc version confirmed latest-approved; checklist + coverage % attached
|  | BPTR-0498-A01-M3 — Confirm assets folder is collision-free for planned icon filenames | Not Applicable — namespace collision check, no user-facing outcome | Search the assets folder for existing files matching planned names (ic_offline_sync.svg, ic_reconnecting.svg) to prevent silent overwrites | Not Applicable | Not Applicable — file-system search, no DOM event | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable — no component hierarchy affected, this is a filename collision check | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Guard: a conflicting file with the same name must be resolved (renamed/removed) before new icon assets can be added | Not Applicable | Not Applicable | Not Applicable | Not Applicable | DoD: file search returns zero naming conflicts; search result screenshot/log attached
|  | BPTR-0498-A01-M4 — Calculate and log final Requirements Traceability Coverage score | Not Applicable — administrative scoring/sign-off, not a user-facing feature | Calculate coverage % (traced substeps ÷ 4) and log Complete/Partial/Not Complete status against the metric | Not Applicable | Not Applicable — manual ticket update, no DOM event | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Guard: coverage below 90% (floor) blocks Complete status — missing approvals must be gathered first | Not Applicable | Not Applicable | Not Applicable | Not Applicable | DoD: ticket updated with coverage %, status field, and checklist attached; peer review of the calculation completed